TESTING AND REMEDIATION PLAN

NCA Statistical & Provider Management Platform

Branch: testing_fix

Prepared: 29 July 2026

Source baseline: NCA Complete Testing Guide v1.0 (34 UAT cases)

Review feedback: Provider workflows, CSV compatibility, viewer access, Broadcasting, rollout readiness

Change gate: This document must exist and pass available QA before source code changes

Decision gate. Resolve tenant isolation and provider workflow defects before releasing feature additions. No live Hugging Face deployment is in scope; all implementation stays on testing_fix.

# 1. Executive Summary

Testing against the supplied guide and rollback-only API probes confirmed two release-blocking defects: provider upload requests omit authentication, and provider users can retrieve another provider's submission records. Submission readiness is also not enforced: the backend accepted a submission at 35% completion.

CSV generation returns data, but download compatibility and spreadsheet safety need strengthening. The proposed NCA Viewer role and sector classification are feature additions scheduled only after the critical workflow and security work.

# 2. Confirmed Findings and Priorities

| Priority | Finding | Evidence | Required outcome |
| --- | --- | --- | --- |
| P0 | Cross-provider data exposure | Provider received HTTP 200 for MTN expected-submission and submission detail. | Return 404 outside the user's organization; cover every related endpoint. |
| P0 | Unauthenticated provider uploads | Authenticated Excel upload returned 201; the frontend-equivalent request returned 401. | Authenticated multipart client, refresh support, server error display. |
| P1 | Submission completeness bypass | Submit-to-approver succeeded at 35% completion. | Central readiness service enforced by API and UI. |
| P1 | KMZ requirement mismatch | Frontend hardcodes requirement ID 1 and never loads real uploads. | Expose section requirements and use returned identifiers. |
| P1 | CSV compatibility risk | CSV returned without UTF-8 BOM/charset; URL is revoked immediately. | BOM, safe headers, formula protection, delayed cleanup. |
| P1 | Smoke-test coverage defect | CSV smoke test depends on undefined PERIOD_ID and sends the wrong payload. | Use the actual filters contract and always execute the test. |
| P2 | View-only role missing | Only four roles exist. | Add NCA_VIEWER plus method-aware permissions and capabilities. |
| P2 | Broadcasting hidden in seeded flows | PAY_TV/DC-TB02 exist, but StarTimes and Broadcasting submissions are excluded by seed slicing. | Add sector classification and category-matched seed coverage. |
| P2 | No automated backend tests | Django discovered zero tests. | Add DRF regression coverage for security, workflow, roles, exports, and sectors. |

# 3. Implementation Workstreams

## 3.1 Provider workflow and tenant isolation

Create shared organization-scoped query helpers for expected submissions, submission versions, values, uploads, downloads, and workflow actions.

Return 404 for provider access outside the user's organization; retain authorized NCA-wide access.

Restrict start, save, upload, submit, return, and official-submit actions by organization, role, and workflow state.

Replace raw multipart requests with an authenticated upload helper that refreshes expired tokens without setting a manual Content-Type boundary.

Expose actual KMZ requirements and uploaded-file lists; remove the hardcoded requirement ID.

Centralize readiness validation for required scalar fields, fixed grids, repeatable-row cells, explanations, and required KMZ uploads.

## 3.2 CSV export compatibility

Allowlist and validate export filters instead of passing arbitrary keys to the ORM.

Emit UTF-8 with BOM, charset, safe attachment filenames, consistent rows, and spreadsheet-formula neutralization.

Create an authenticated download helper that validates response type, attaches the temporary link, and revokes the object URL after the click completes.

Repair the shell smoke test to use the real filters payload and remove the undefined period condition.

## 3.3 NCA Viewer

Add NCA_VIEWER to the database, serializers, type definitions, labels, administrator user creation, and login routing.

Expose explicit capabilities from /auth/me/ and use them to remove write controls.

Allow Dashboard, Providers, Submissions, Periods, Compliance, Exports, and CSV download access.

Deny review, compliance actions, configuration, uploads, user management, and form management at the backend.

## 3.4 Broadcasting visibility

Add TELECOM/BROADCASTING sector fields to providers and form templates.

Data-migrate PAY_TV and DC-TB02 to Broadcasting; map existing remaining records to Telecom.

Expose sector filters and labels in operational views and CSV exports.

Repair seed assignment so StarTimes and DC-TB02 generate category-matched test submissions.

Do not fabricate additional production statistics; future templates depend on authoritative NCA data definitions.

# 4. Delivery Phases and Owners

| Phase | Workstream | Owner | Exit evidence | Gate |
| --- | --- | --- | --- | --- |
| 0 | Document gate | Engineering lead | Plan DOCX created; render attempted; structural audit completed. | Before code |
| 1 | Security and provider workflow | Backend + frontend engineering | P0/P1 workflow tests pass; no cross-tenant access. | Release blocker |
| 2 | CSV compatibility | Backend + frontend engineering | Browser and spreadsheet matrix passes. | Release blocker |
| 3 | Viewer and sector support | Engineering + product owner | Role/capability and Broadcasting acceptance tests pass. | Feature gate |
| 4 | UAT and release readiness | QA lead | 34-case matrix signed with zero critical/high failures. | Release gate |
| 5 | Communications rollout | Corporate Communications lead | Release notes, publication schedule, and sign-off recorded. | Launch gate |
| 6 | Remote-test readiness | NCA IT/Network Support | Connectivity preflight, fallback channel, recording, and incident log ready. | Test-session gate |

# 5. Acceptance Criteria

Provider users cannot enumerate or access another provider's submissions, values, or files.

Valid provider uploads succeed and appear immediately; expired tokens refresh; invalid files show actionable errors.

Incomplete submissions return INCOMPLETE_SUBMISSION with structured blockers; complete submissions transition correctly.

Provider Approvers can review and submit only their organization's pending submissions.

CSV downloads open without mojibake in supported browsers, Microsoft Excel, and Google Sheets.

NCA Viewer can read operational modules and export data but cannot mutate operational or administrative records.

Broadcasting is independently filterable and the StarTimes/DC-TB02 test flow is present.

All automated checks pass and the 34-case UAT matrix has zero critical/high failures.

# 6. Operational Release Checklists

## 6.1 Corporate Communications

Assign a Communications owner for each release.

Prepare plain-language release notes, screenshots, key milestones, and publication dates.

Review accuracy with the product owner and record Communications sign-off.

Coordinate internal notice and public-channel publication only after QA release approval.

## 6.2 IT and remote testing

Run connectivity and audio checks before remote UAT sessions.

Publish a fallback meeting link or dial-in route and a named support contact.

Record approved sessions and retain an incident log with interruption times and resolutions.

Reschedule affected test cases when connectivity prevents reliable evidence capture.

# 7. UAT Traceability Matrix

| Test ID | Module | Priority | Baseline evidence | Acceptance |
| --- | --- | --- | --- | --- |
| UAT-001 | Authentication | P2 | Re-run required | Valid login reaches role dashboard. |
| UAT-002 | Authentication | P2 | Re-run required | Bad credentials are rejected. |
| UAT-003 | Authentication | P2 | Re-run required | Logout prevents protected navigation. |
| UAT-004 | Dashboard | P2 | Re-run required | Dashboard counts and alerts load. |
| UAT-005 | Dashboard | P2 | Re-run required | Notification panel loads relevant items. |
| UAT-006 | Providers | P2 | Re-run required | Provider list shows required columns. |
| UAT-007 | Providers | P2 | Re-run required | Vodafone search filters correctly. |
| UAT-008 | Providers | P2 | Re-run required | MNO filter returns MNO records. |
| UAT-009 | Providers | P2 | Re-run required | Provider detail loads. |
| UAT-010 | Providers | P2 | Re-run required | Provider sees only own organization. |
| UAT-011 | Submissions | P2 | Re-run required | Submission list and statuses load. |
| UAT-012 | Submissions | P2 | Re-run required | Provider search filters results. |
| UAT-013 | Submissions | P2 | Re-run required | DRAFT filter returns only drafts. |
| UAT-014 | Provider workflow | P1 | Re-run required | Provider starts an assigned form. |
| UAT-015 | Provider workflow | P1 | Re-run required | Saved values persist. |
| UAT-016 | Provider workflow | P1 | Re-run required | Non-applicable status and explanation persist. |
| UAT-017 | Provider workflow | P1 | Re-run required | Section navigation and progress update. |
| UAT-018 | Provider workflow | P0 | FAIL: client omits JWT; direct authenticated API passes | Authenticated Excel upload is listed. |
| UAT-019 | Provider workflow | P0 | FAIL: readiness not enforced | Complete form becomes PENDING_APPROVAL. |
| UAT-020 | Approval workflow | P0 | Backend transition passes; UI re-run required | Approver submits own pending form to NCA. |
| UAT-021 | Approval workflow | P1 | Re-run required | NCA approval moves form to APPROVED. |
| UAT-022 | Approval workflow | P1 | Re-run required | Correction request reopens provider editing. |
| UAT-023 | Compliance | P2 | Re-run required | Compliance list loads. |
| UAT-024 | Compliance | P2 | Re-run required | Open flag becomes acknowledged. |
| UAT-025 | Compliance | P2 | Re-run required | Acknowledged flag resolves. |
| UAT-026 | Compliance | P2 | Re-run required | Provider email draft includes details. |
| UAT-027 | Compliance | P2 | Re-run required | Provider sees own compliance data only. |
| UAT-028 | Users | P2 | Re-run required | Admin creates a valid user. |
| UAT-029 | Users | P2 | Re-run required | Admin deactivates/reactivates user. |
| UAT-030 | Users | P2 | Re-run required | Provider user links to organization. |
| UAT-031 | Exports | P1 | API returns CSV; compatibility re-run required | CSV downloads successfully. |
| UAT-032 | Exports | P1 | API contains rows; Excel/Sheets re-run required | CSV contains submitted values. |
| UAT-033 | Security | P1 | Re-run required | Provider is denied NCA routes. |
| UAT-034 | Security | P0 | FAIL: cross-provider detail returned HTTP 200 | Changed submission ID returns 404/403. |

# 8. Verification Commands and Evidence

Django system checks and complete Django test suite.

TypeScript compiler with --noEmit and production Next.js build.

Corrected API smoke suite against the local testing_fix services.

Role-by-role manual UAT with screenshots/download evidence for failed or high-risk cases.

Final git diff review confirming no unrelated changes and no secrets or generated local data are tracked.

# 9. Assumptions and Boundaries

Only testing_fix is modified; the live Hugging Face deployment is excluded.

NCA Viewer covers operational modules and CSV export but excludes Form Builder and User Management.

Broadcasting work exposes existing Pay TV foundations without inventing authoritative production statistics.

Local SQLite, dependency stores, logs, and generated test files remain untracked.

If LibreOffice remains unavailable, structural DOCX QA is the documented fallback for this plan artifact.